PROGETTO PIT.AGORA' – PROGRAMMA LEONARDO D.V. TOI 2010

CUP Code: G12F10000140006

WP 5 – EXPERIMENTATION

PROGRAM OF EXPERIMENTATION

| STEP 1 |
| --- |
| Training and training in self-learning |
| times | from October 2011 to November 2011 |
|  | The trainers and teachers involved in the project complete their training using materials and information provided at the end of training sessions and eventually requiring the support of the Garden of Archimedes via computer or telephone. |

| STEP 2 |
| --- |
| Programming Laboratory |
| times | from October 2011 to November 2011 |
|  | Teachers involved in the project programm each of the laboratories to perform in the classes. This programming must be registered in Part 1 of "MONITORING AND EVALUATION EXPERIMENT" along with Part 0 of the same card. Send the form filled in Part 0 and 1 to the Garden of Archimedes via email or through the forum in the site of the Project (if enabled). This item must precede the experimentation in class. |

| STEP 3 |
| --- |
| Experimenting laboratories in the classroom |
| times | by February 2012 |
|  | Each teacher proceeds with experiment laboratories in the class following the planned program approved by The Garden of Archimedes. After the experimentation in the classroom: make the report of this activity by filling in Part 2 of "MONITORING AND EVALUATION EXPERIMENT". Send it to the Garden of Archimedes by e-mail or through the forum in the site of the Project (if enabled). |

| STEP 4 |
| --- |
| Suggestions for changes in laboratory |
| times | from October to February 2012 |
|  | Each teacher can provide suggestions for changes to the materials of laboratory. These suggestions can be provided by completing the "FORM FOR ADAPTATION AND CHANGE" and sent to the Garden of Archimedes by e-mail or through the forum of the Project (if enabled) at any time of experimentation. |

| STEP 5 |
| --- |
| Collecting information on the effects |
| times | from October to February 2012 |
|  | Each teacher collects information on references to activities on time after the proposed activities in the classroom. With such information complete part 3 of "MONITORING AND EVALUATION EXPERIMENT" and sent it to the Garden of Archimedes by e-mail or through the use of the forum project (if enabled), at any time of the experimentation. |

| FASE 6 |
| --- |
| Results of experiments |
| times | by March 2012 |
|  | Each teacher should complete Part 4 of "MONITORING AND EVALUATION EXPERIMENT," according to the instructions and send it to the Garden of Archimedes by e-mail or through the forum of the Project (if enabled). |